# Day 4 Assignment: Early Integration Strategy

Pet Service Platform — AI Knowledge Q&A Module

## 1. Hot KPP Selection

Based on the incremental integration analysis, the Requirements Certainty of AI Pet Knowledge Q&A Module is selected as the hot KPP.

Rationale: Among all KPPs tracked across the integration sequence (M0-M5), this metric shows the highest uncertainty spike—from 95% certainty at M3 (Message Module) to only 70% at M4 (AI Module). This 25% drop indicates significant unknowns that threaten project success if not addressed early.

| KPP Dimension | M3 (Message Module) | M4 (AI QA Module) |
| --- | --- | --- |
| Requirements Certainty | 95% — Clear scope | 70% — Fuzzy boundaries |
| Technical Risk | Medium — Known tech | High — External dependency |
| Integration Status | Verified | Partially Verified |

## 2. Two Critical Assumptions That Could Cause KPP Failure

Assumption 1: AI Interface Response Time

- Statement: The AI Q&A API can respond within 3 seconds for 95% of requests.

- Failure scenario: If actual response time is 5-10 seconds, user experience becomes unacceptable, leading to feature abandonment.

- Root cause: External AI service latency, network instability, or complex query processing time underestimated.

Assumption 2: AI Answer Accuracy

- Statement: The AI can provide accurate and relevant answers to pet-related questions with ≥80% accuracy.

- Failure scenario: If accuracy drops below 70%, users lose trust, and the feature becomes a liability rather than an asset.

- Root cause: Knowledge base scope unclear; AI model not fine-tuned for pet domain; ambiguous user questions.

## 3. Proposed Early Integration Increment: M3.5 AI Prototype

Rather than waiting until M4 to integrate the full AI module, we insert an early integration increment (M3.5) between M3 and M4 specifically designed to expose risks.

M3.5 Scope (Minimum Viable Integration):

- Backend: AI API integration with basic request/response handling

- Test harness: 50 predefined pet-related questions covering common scenarios

- No full knowledge base or frontend UI—focus purely on API validation

- Duration: 3-5 days (short, time-boxed)

Why this exposes risk early:

- Tests the highest-risk component (AI API) before committing to full development

- Provides concrete data on response time and accuracy within one week

- If assumptions fail, we can pivot early—switch AI providers, adjust scope, or implement fallback strategies

## 4. Validation Activity: Comprehensive AI API Stress Testing

| Test Category | Methodology | Pass Criteria |
| --- | --- | --- |
| Response Time Test | Send 500+ requests with varied question complexity; measure P50, P95, P99 response times | P95 ≤ 3 seconds; P99 ≤ 5 seconds |
| Accuracy Assessment | 50 predefined questions with expert-verified answers; blind evaluation by 3 reviewers | ≥80% rated as accurate and helpful |
| Fault Injection | Simulate API timeout (10s), rate limiting (429 error), and service unavailable (503) | System degrades gracefully; user sees helpful error message |
| Load Test | 100 concurrent users sending requests for 10 minutes | No degradation in response time; error rate < 1% |

## 5. Expected Learning from This Step

Technical Feasibility:

- Can the AI API meet performance requirements? If not, we need to explore caching, pre-computation, or alternative providers.

Requirements Refinement:

- What types of questions does the AI handle well? Where does it fail? This informs knowledge base scope and user guidance.

Integration Risk Assessment:

- Are there hidden coupling issues between AI module and existing user system? Early detection prevents late-stage refactoring.

Decision Point:

- Go/No-Go: If both assumptions pass, proceed to full M4 development. If either fails, implement contingency plans before committing resources.

Contingency Plans (if assumptions fail):

- Response time > 3s: Implement local caching + fallback to FAQ database

- Accuracy < 80%: Narrow knowledge scope to high-confidence topics; add human review loop

- API unreliable: Switch to backup AI provider or hybrid approach (AI + rule-based)